|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **BASSA**  BassaNet  c/o WORIWA Office  Buchanan City  13 member organizations, some of which are CBOs  Partnering with three [3] CBOs to implement the Community Livelihood Support Project | BassaNet Community Livelihood Support Project | US$10,000.00 | Zardun Mother’s Club, District 3, Tubmanville (R&S)   * 35 members, comprising mostly women, some men and youths * Establish a village savings and Loan association that has increased from 15 members to a present 75 members that now includes women from the wider Zardun community * Obtained a cassava processing machine for gari production * Produce *‘kabacru’* soap for the local market as far as Buchanan   Deh-do-yeajay, District 3, Besaymah, Lower Buchanan (WORIWA)   * 30 members, mainly women and youths   Liberia United Disabled Society District 3 Wayzohn (AEL)   * 35 members, most of whom are blind men and women; there are few youths * Gained knowledge from leadership training and soap production * Did vegetable and peanuts farming, and divided proceeds among members | **First Milestone**   * Submission of concept and budget * Submission of completed assessment results * Submission of all outstanding reports (Assembly report, minutes, etc.) * Approval of monitoring plan   **Total amount**  $7,500.00  **Second Milestone**  **(After 3 months into implementation)**   * Midterm project report * Monitoring report * Plan for submission of final project report   **Total amount**  $2,500.00 |
| **BONG**  BongoNet  c/o Refound Office  Gbarnga City  16 member organizations, some of which are CBOs  Partnering with four [4] CBOs to implement the Community Livelihood Support Project | BongoNet Community Livelihood Support Project  Empowering Vulnerable Cooperative Farmers in Rural Communities | US$10,000.00 | Suayelle Multi-Purpose Corporation SUAYEMCO  Gbartala Town, Yellequelleh District   * 1,250 members, both men and women located across two districts: Suakoko and Yellequelleh * Involved in cooperative farming (Kuu), where they grow mainly rice and corn, for commercial purpose. They have their own plot of land   Kukatornon Women Group  Palala Town, Kpaai district   * 27 members, all of whom are women, mostly widows and single mothers * Involved in VSLA activities and cultivation of corn, peanuts and vegetables   Kukatornon Cooperative Group  Foequelleh Town, Panta District   * 64 members, both men and women * Involved cultivation of corn and rice for commercial purposes * This group meets on Sundays during the afternoon hours * They are leasing the land on which they cultivate their crops (official leasing contract)   Nyallafamah Cooperative Group  Gbantah Community  Jorquelleh District   * 45 members, mainly men and women * They cultivate plantains and vegetable crops for commercial purpose; they are also into VSLA ventures | **First Milestone**   * Submission of concept and budget * Submission of completed assessment results * Submission of all outstanding reports (Assembly report, minutes, etc.) * Approval of monitoring plan   **Total amount**  $7,500.00 (from which shall be deducted NARDA’s outstanding dues)  **Second Milestone**  **(After 3 months into implementation)**   * Midterm project report * Monitoring report * Plan for submission of final project report   **Total amount**  $2,500.00 |
| **LOFA**  **LofaNet**  c/o VOWODPEDE Office  Voinjama City  28 members, most of which are women’s groups and CBOs  Partnering with four [4] CBOs to implement the Community Livelihood Support Project | LOFANET– Community Livelihood Support Project | US$10,000.00 | Barkedu FOI Women Group  Quadougboni District   * 50 members including widows and single mothers * Involved in cultivation of peanuts, pepper, bitter balls, and other garden crops; also in saving clubs for revolving funds to help the needed. Finally, they are nearing the completion of their women’s center * This group meets on every Friday   Wenlai (Love), commonly called Lazelemai Women Group  Lazelemai Town, Voinjama District   * 40 members, mostly single mothers and widows * Involved in cultivation of rice, beans, peanuts, and plantains, for commercial purpose; group also has some assets that need repair in order to effectively use them * This group meets on Saturday mornings   Sembehill (meaning Be Serious)  Massabolahun Town, Wanhasa District   * 125 members, most of whom are women * Involved into weaving of country cloth, cultivation of peanuts, and beans for commercial purpose * This group meets on Fridays   Vezala FOI Women Group  Vezala Town, Voinjama District   * 50 members, all women, mostly widows and single mothers * Involved with cultivation of oil palm, weaving and tie &dye production, peanuts and beans farming * This group meets on Fridays | **First Milestone**   * Submission of concept and budget * Submission of completed assessment results * Submission of all outstanding reports (Assembly report, minutes, etc.) * Approval of monitoring plan   **Total amount**  $7,500.00 (from which shall be deducted NARDA’s outstanding dues)  **Second Milestone**  **(After 3 months into implementation)**   * Midterm project report * Monitoring report * Plan for submission of final project report   **Total amount**  $2,500.00 |
| **NIMBA**  **NimbaNet**  C/O ARS Office  Sanniquellie City  17 members, some of which are CBOs  Partnering with four [4] CBOs to implement the Community Livelihood Support Project | Nimba Net (NNN) Community livelihood support project (CLSP) | US$10,000.00 | Visually impaired /physically challenged  Sanniquellie Mahn District   * 25 members all of whom are visually impaired * Involved in cultivation of cassava and peanuts, as well as production of soap * This group meets on Saturdays, evening hours   Zordordelah Elderly/widow group  Zorpata Town, Gbelaygeh District   * 34 members * Involved in cultivation of beans, peanuts, corn, for commercial purpose * This group meets on Saturdays   Try and See Agriculture group  Gboiyellah Town, Sanniquellie Mahn District   * 25 members * Involved in cultivation of rice, peanuts, eddoes and beans for commercial purpose * This group meets on Fridays   Concern women Group  Tonglawin, Ganta, Bain-Gah district   * 25 members, all women, mostly widows and single mothers * Involved with cultivation of cassava on a large scale for production of different cassava products * This group meets on Fridays and Saturdays | **First Milestone**   * Submission of concept and budget * Submission of completed assessment results * Submission of all outstanding reports (Assembly report, minutes, etc.) * Approval of monitoring plan   **Total amount**  $7,500.00 (from which shall be deducted NARDA’s outstanding dues)  **Second Milestone**  **(After 3 months into implementation)**   * Midterm project report * Monitoring report * Plan for submission of final project report   **Total amount**  $2,500.00 |
| SINOE  SinoeNet  c/o NIPO Office  Greenville City  11 Members, some of which are women’s groups and CBOs  Partnering with three [3] CBOs to implement the Community Livelihood Support Project | SinoeNet Community Livelihood Support Project | US$10.000.00 | Come and see, Kabada  Kpanyan, District.   * 45 members, comprising mostly women, men, youths, and elders. * Establish a susu association. * Obtained a cassava farm for the productions of gari and fufu. * Involve in adult literacy school.   Friend - O- Friend, Kabada  Kpanyan District.  - 40 members, comprising mostly of youth, women, and elders.   * Establish a susu association. * Obtained a cassava farm for the productions of gari and fufu. * Involve in adult literacy school.   Mayannobo United Farmers Saving Club, Compound, Butaw District.   * 36 members, comprising mostly of youth, men, and women. * Establish village saving loan association. | First Milestone   * Submission of concept and budget * Submission of completed assessment results. * Submission of all outstanding reports (Assembly report, minutes, etc.) * Approval of monitoring plan   Total amount  $7,500.00 (from which shall be deducted NARDA’s outstanding dues)  Second Milestone  (After 3 months into implementation)   * Midterm project report * Monitoring report * Plan for submission of final project report   Total amount  $2,500.00 |